SOFTWARE & WEB APPLICATION PROTECTION SYSTEM License Verification System PROJECT PLAN • MVP SPECIFICATION • IMPLEMENTATION ROADMAP Version 1.0 ¦ February 2026

# Executive Summary

The Software & Web Application Protection System (SWAPS) is a centralized license validation platform designed to protect desktop and web applications from unauthorized use. This document outlines the complete project plan, MVP scope, sprint breakdown, and technical implementation strategy.

| 16 Weeks Project Duration | 8 Sprints Total Sprints | Week 8 MVP Delivery | FastAPI + PostgreSQL Tech Stack |
| --- | --- | --- | --- |

# 1. Project Overview

## 1.1 Objectives

- Generate unique, cryptographically-secure license keys for each application deployment

- Allow developers to embed a secret key directly into their applications with minimal integration effort

- Automatically validate license status on the 26th day of each month at 12:00 AM via a secure API call

- Disable or restrict application functionality when a license becomes invalid, expired, or revoked

- Provide a full admin dashboard for license lifecycle management

## 1.2 System Architecture

High-Level Architecture

Protected Application (Desktop/Web) ¦ ¦ Monthly Validation Request (HTTPS + HMAC) ¦ Protection Server (FastAPI REST API) ¦ ¦ Validate Key + Expiry + Status ¦ PostgreSQL Database (License Storage) ¦ ¦ Audit Log + Alert System ¦ Admin Dashboard (React / Jinja2)

## 1.3 Core Components

| Component | Description |
| --- | --- |
| License Management Server | FastAPI backend that generates, stores, and validates license keys. Central authority for all license decisions. |
| Admin Dashboard | Web-based management interface for creating, editing, and monitoring licenses and validation history. |
| Client SDK (Python Package) | Lightweight Python package embedded in protected apps. Handles scheduled validation, key storage, and enforcement. |
| PostgreSQL Database | Stores license records, client info, validation history, and audit logs with full encryption. |
| Scheduler / CRON Engine | Triggers validation calls on the 26th of each month at 12:00 AM in the client app timezone. |

# 2. MVP Specification

The MVP (Minimum Viable Product) focuses on delivering a fully functional, end-to-end license validation system in 8 weeks. Post-MVP enhancements add analytics, multi-app support, and advanced security features.

## 2.1 MVP Feature Set

| Feature | Priority | Sprint | Effort |
| --- | --- | --- | --- |
| License Key Generation (HMAC-SHA256) | Critical | S1 | 3 days |
| License CRUD API (Create, Read, Update, Deactivate) | Critical | S1-S2 | 4 days |
| PostgreSQL Schema + Migrations (Alembic) | Critical | S1 | 2 days |
| JWT Admin Authentication | Critical | S2 | 3 days |
| License Validation Endpoint (/validate) | Critical | S2 | 3 days |
| Client SDK - Core (Python Package) | Critical | S3 | 5 days |
| Client SDK - Scheduler (26th/month trigger) | Critical | S3 | 2 days |
| Client SDK - App Lock / Restriction Logic | High | S4 | 3 days |
| Admin Dashboard - License Management | High | S4-S5 | 5 days |
| Validation History & Audit Log | High | S5 | 3 days |
| HTTPS + SSL (Let's Encrypt via Nginx) | High | S6 | 1 day |
| Docker Compose Deployment | High | S6 | 2 days |
| Unit Tests (80% coverage target) | High | S7 | 4 days |
| Integration Tests & Validation Scenarios | High | S7 | 3 days |
| Developer Integration Guide & SDK Docs | High | S8 | 2 days |
| UAT + Bug Fixes | High | S8 | 3 days |

## 2.2 Out of Scope (MVP)

The following features are excluded from the MVP and are planned for post-launch iterations:

- Multi-tenant architecture (multiple admin organizations)

- Real-time analytics dashboard with usage graphs

- Webhook notifications on license events

- SDK clients for languages other than Python (Node.js, .NET, Java)

- Offline grace period with cryptographic offline tokens

- Hardware fingerprint / machine binding

- White-label/customizable branding per client

# 3. Sprint Plan (16-Week Roadmap)

The project is organized into 8 two-week sprints. Sprints 1-4 build the core infrastructure; Sprints 5-6 complete the full feature set; Sprints 7-8 cover testing, deployment, and documentation.

| Phase | Name | Duration | Focus |
| --- | --- | --- | --- |
| Sprint 1 | Foundation & Database | Weeks 1-2 | Project setup, DB schema, key generation, core models |
| Sprint 2 | API Core & Auth | Weeks 3-4 | JWT auth, license CRUD APIs, validation endpoint |
| Sprint 3 | Client SDK | Weeks 5-6 | Python SDK, scheduler, key storage, API integration |
| Sprint 4 | Enforcement & Dashboard | Weeks 7-8 | App lock logic, admin UI (MVP milestone) |
| Sprint 5 | Admin Dashboard II | Weeks 9-10 | Audit logs, validation history, license search/filter |
| Sprint 6 | Deployment & Security | Weeks 11-12 | Docker, Nginx, SSL, rate limiting, hardening |
| Sprint 7 | Testing | Weeks 13-14 | Unit tests, integration tests, load testing, security scan |
| Sprint 8 | Docs & Release | Weeks 15-16 | SDK docs, dev guide, UAT, production deployment |

## 3.1 Sprint 1 — Foundation & Database (Weeks 1-2)

### Goals

- Initialize project repository with Git branching strategy (main / develop / feature/*)

- Set up FastAPI project skeleton with folder structure and dependency management (Poetry)

- Design and implement PostgreSQL schema with Alembic migration tooling

- Implement HMAC-SHA256 license key generation algorithm

- Configure Docker development environment

### Database Schema — Core Tables

| Table | Key Fields |
| --- | --- |
| licenses | id, license_key (hashed), app_name, client_name, expiry_date, status, created_at, monthly_renewal |
| applications | id, name, description, owner_email, created_at |
| validation_logs | id, license_id, validated_at, ip_address, result (success/fail), error_reason |
| admins | id, email, password_hash, role, last_login, is_active |

## 3.2 Sprint 2 — API Core & Authentication (Weeks 3-4)

### API Endpoints (MVP)

| Endpoint | Description |
| --- | --- |
| POST /auth/login | Admin login — returns JWT access + refresh tokens |
| POST /licenses/ | Create a new license (admin only) |
| GET /licenses/ | List all licenses with filters (admin only) |
| GET /licenses/{id} | Get single license details |
| PATCH /licenses/{id} | Update license fields (status, expiry, etc.) |
| DELETE /licenses/{id} | Soft-delete / deactivate a license |
| POST /licenses/validate | Public endpoint — validates a license key (called by SDK) |
| GET /licenses/{id}/history | Get validation history for a license |

## 3.3 Sprint 3 — Client SDK (Weeks 5-6)

### SDK Package Structure

Python SDK — app_protection/

app_protection/ __init__.py # Public API: protect(), validate_now() client.py # HTTP client for validation API scheduler.py # APScheduler: 26th/month 12:00 AM trigger storage.py # Secure local key storage (keyring / env) enforcer.py # App lock / restriction logic exceptions.py # LicenseExpiredError, ValidationFailedError config.py # Server URL, retry settings setup.py # Package distribution

### Integration Example (Developer Code)

Developer Integration — 3 Lines of Code

from app_protection import protect # Called at app startup — validates once, then schedules monthly checks protect( license_key='LIC-XXXX-XXXX-XXXX-XXXX', server_url='https://protection.yourserver.com', on_invalid=lambda: disable_app_features() # Your enforcement callback )

# 4. Technical Specifications

## 4.1 Technology Stack

| Layer | Technology & Rationale |
| --- | --- |
| Backend Framework | FastAPI (Python 3.11+) — async-first, auto-generated OpenAPI docs, high performance |
| Database | PostgreSQL 15 — ACID compliance, JSON support, mature ecosystem |
| ORM | SQLAlchemy 2.0 + Alembic — async ORM with migration support |
| Authentication | JWT (access: 15min, refresh: 7d) via python-jose + passlib |
| Key Security | HMAC-SHA256 for key generation; keys stored as salted hashes, never plaintext |
| Client Scheduler | APScheduler 3.x — lightweight Python job scheduler, cron-style triggers |
| Local Key Storage | Python keyring library — OS-native secure storage (Keychain / Credential Manager) |
| Containerization | Docker + Docker Compose — reproducible environments across dev/staging/prod |
| Reverse Proxy | Nginx — SSL termination, rate limiting (100 req/min per IP), static serving |
| SSL | Let's Encrypt via Certbot — free auto-renewing certificates |
| Admin UI | Jinja2 templates + HTMX (server-side rendered, minimal JS complexity) |
| Testing | pytest + httpx (async) + pytest-cov — targeting 80%+ coverage |
| CI/CD | GitHub Actions — lint (ruff), test, build Docker image on push to develop/main |

## 4.2 Security Design

### License Key Format

Key Structure

LIC-{APP_CODE}-{TIMESTAMP_HEX}-{HMAC_TRUNCATED} Example: LIC-MYAPP-018E2F3A-7B9D2C1E4F5A6B8C Generation: HMAC-SHA256(secret_seed + app_id + timestamp) truncated to 16 hex chars Storage: Only SHA256 hash of key stored in DB — original key shown once at generation

### Validation Security

- All validation requests signed with HMAC-SHA256 (request body + timestamp + shared secret)

- Replay attack prevention: timestamp in request must be within 5-minute window

- Rate limiting: 10 validation requests per license key per hour

- Validation endpoint returns minimal information to prevent enumeration attacks

- All API traffic over HTTPS (TLS 1.2+ minimum, TLS 1.3 preferred)

# 5. Detailed Functional Requirements

## 5.1 License Lifecycle

| Status | Behavior |
| --- | --- |
| Active | Validation passes — application runs normally |
| Inactive | Validation fails immediately — application blocked |
| Expired | Validation fails if past expiry_date — application blocked |
| Suspended | Temporary block — can be reactivated by admin without new key |
| Pending | Created but not yet activated — validation returns pending state |

## 5.2 Validation Flow

- Client SDK scheduler triggers on the 26th of the month at 12:00 AM local time

- SDK retrieves stored license key from OS keyring / environment variable

- SDK constructs signed validation request: {license_key, timestamp, app_id, HMAC_signature}

- Request sent via HTTPS POST to /licenses/validate on the Protection Server

- Server verifies HMAC signature, timestamp freshness, and replay protection

- Server queries DB: checks license_key hash, status, expiry_date

- Server records result in validation_logs table

- Server returns JSON: {valid: bool, status: string, expires_at: datetime, message: string}

- SDK receives response. If valid=true: schedules next check. If valid=false: calls on_invalid() callback

- If network unreachable: SDK retries 3x with 5-minute backoff, then enters grace period (48 hours)

# 6. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| License key interception during transit | Low | High | HTTPS + HMAC signing on all requests; key never transmitted in plaintext after generation |
| Validation server downtime blocks clients | Medium | High | 48-hour grace period in SDK; load balancing; uptime monitoring with PagerDuty alerts |
| SDK reverse engineering exposes secret | Medium | Medium | Server-side validation is authoritative; even if SDK is bypassed, API requires valid HMAC |
| Database breach exposes license data | Low | High | Keys stored as hashes; DB encrypted at rest; VPC isolation; principle of least privilege |
| Scope creep extends timeline | High | Medium | Strict MVP scope; feature requests logged to backlog; bi-weekly stakeholder reviews |
| Developer adoption friction | Medium | Medium | SDK designed for 3-line integration; comprehensive docs; example projects provided |

# 7. Post-MVP Roadmap

## Phase 2 — Enhanced Security & Analytics (Months 5-6)

- Hardware fingerprint / machine binding for stricter enforcement

- Offline cryptographic tokens (signed JWT with TTL for air-gapped environments)

- Real-time analytics dashboard: validation rate, geographic distribution, failure trends

- Webhook system: license events (expiry, failure, renewal) POST to developer-defined URLs

## Phase 3 — Multi-Language SDK & Scalability (Months 7-9)

- SDK clients for Node.js, Java, .NET, Go, and PHP

- Multi-tenant architecture: separate organizations with isolated license namespaces

- Horizontal scaling: Redis caching for validation results, read replicas for DB

- SLA: 99.9% uptime target with automated failover

## Phase 4 — Enterprise Features (Months 10-12)

- White-label dashboard with custom branding per enterprise client

- SAML/SSO integration for enterprise admin authentication

- License metering / usage-based licensing (API call counting)

- Compliance reporting: SOC 2 audit log export, GDPR data management tools

# 8. Success Metrics & Definition of Done

## 8.1 MVP Acceptance Criteria

- License key generation produces unique, non-guessable keys 100% of the time

- Validation API responds in under 200ms (p95) under normal load

- Client SDK successfully triggers validation on the 26th of the month within a 1-minute window

- Admin can perform full license lifecycle management via dashboard without engineering support

- System correctly blocks application access within 60 seconds of license invalidation

- All API endpoints protected by JWT authentication with proper role enforcement

- 80%+ unit test coverage on server-side code

- Deployment reproducible from scratch in under 30 minutes using Docker Compose

## 8.2 Technical KPIs

| Metric | Target |
| --- | --- |
| Validation API latency (p95) | < 200ms |
| System uptime | > 99.5% |
| Test coverage | > 80% |
| SDK integration time | < 30 minutes for developer |
| License key collision probability | < 1 in 10^38 (cryptographically negligible) |
| Validation replay window | 5 minutes maximum |
| Grace period on server unreachable | 48 hours |

# Appendix: Folder Structure

Project Repository Structure

swaps/ ├── server/ # FastAPI backend │ ├── app/ │ │ ├── api/routes/ # Endpoint handlers │ │ ├── core/ # Config, security, DB │ │ ├── models/ # SQLAlchemy ORM models │ │ ├── schemas/ # Pydantic request/response schemas │ │ ├── services/ # Business logic │ │ └── templates/ # Jinja2 admin dashboard │ ├── migrations/ # Alembic DB migrations │ └── tests/ # pytest test suite ├── sdk/ # Python client SDK │ └── app_protection/ ├── deploy/ # Docker & Nginx configs │ ├── docker-compose.yml │ ├── nginx/nginx.conf │ └── certbot/ └── docs/ # Developer guides & API reference